## Team_Mapping
Batch | Team | Member Name | Role | Week | Scrum Master?
Batch 1 | Team 3 | Iyas K | DevOps Engineer | Week 1 | Yes
Batch 1 | Team 3 | Muhammed Sinan | DevOps Engineer | Week 1 | No
Batch 1 | Team 3 | Norah Elizabeth Biju | DevOps Engineer | Week 1 | No
Batch 1 | Team 3 | Bhogyam venkata sai Likhitha | DevOps Engineer | Week 1 | No
Batch 1 | Team 3 | Ogeti Aravind | DevOps Engineer | Week 1 | No
Batch 1 | Team 3 | Mahesh D | DevOps Engineer | Week 2 | Yes

## Sprint-Overview
Sprint | Sprint Goal | Start Date | End Date | Deliverable
Sprint 1 | Linux & AWS Overview | 2026-02-17 | 2026-02-18 | Understanding Linux commands and AWS Services
Sprint 2 | EC2 Instances & VPC | 2026-02-19 | 2026-02-20 | Hands‑on with EC2 and VPC
Sprint 3 | Load Balancers,Subnets, Internet Gateways & NAT Gateways | 2026-02-21 | 2026-02-23 | Setting Up Load Balancers,Public/Private Subnets with IGW & NAT Gateways
Sprint 4 | RDS & 3-Tier Devops Architecture | 2026-02-24 | 2026-02-25 | Fullstack Monolithic App with Frontend, Backend & RDS in 3-Tier Devops Architecture
Sprint 5 | DevOps Worflow, Hardware Level Virtualization and Containerization | 2026-02-26 | 2026-03-02 | Understanding Devops Worflow, hardware virtualization concepts, disadvantages of VMs and Docker Containerization
Sprint 6 | Docker Networking and Compose | 2026-03-03 | 2026-03-04 | Creating containers and images, custom network
|  | 2026-03-05 | 2026-03-05 | Module 1 evaluation presentation
Sprint 7 | Docker disadvantages and docker swarm | 2026-03-06 | 2026-03-07 | Understanding the disadvantages of Docker containers, and the limitations in Docker Swarm
Sprint 8 | Kubernetes Components and Introduction | 2026-03-09 | 2026-03-10 | Understanding the Kubernetes components, its architecture, how components communicate, api server, setting up our own clusters, deep diving into the workflow behind each command of creating control plane, pods and its life cycle.

## Task_Tracking(23-02)
Sprint | Team | TaskID | Description | AssignedTo | StoryPoint | Status | Reviewer
Sprint 1 | Team 3 | T1-001 | Understand Linux commands and AWS Services | Iyas K | 2 | Done | Trainer
Sprint 1 | Team 3 | T1-002 | Understand Linux commands and AWS Services | Muhammed Sinan | 2 | Done | Norah Elizabeth Biju
Sprint 1 | Team 3 | T1-003 | Understand Linux commands and AWS Services | Norah Elizabeth Biju | 2 | Done | Trainer
Sprint 1 | Team 3 | T1-004 | Understand Linux commands and AWS Services | Bhogyam venkata sai Likhitha | 2 | Done | Mahesh D
Sprint 1 | Team 3 | T1-005 | Understand Linux commands and AWS Services | Ogeti Aravind | 2 | Done | Trainer
Sprint 1 | Team 3 | T1-006 | Understand Linux commands and AWS Services | Mahesh D | 2 | Done | Iyas K
Sprint 2 | Team 3 | T2-001 | Set up EC2 Instances , Configure VPC & Security groups | Iyas K | 3 | Done | Trainer
Sprint 2 | Team 3 | T2-002 | Set up EC2 Instances , Configure VPC & Security groups | Muhammed Sinan | 3 | Done | Ogeti Aravind
Sprint 2 | Team 3 | T2-003 | Set up EC2 Instances , Configure VPC & Security groups | Norah Elizabeth Biju | 3 | Done | Trainer
Sprint 2 | Team 3 | T2-004 | Set up EC2 Instances , Configure VPC & Security groups | Bhogyam venkata sai Likhitha | 3 | Done | Muhammed Sinan
Sprint 2 | Team 3 | T2-005 | Set up EC2 Instances , Configure VPC & Security groups | Ogeti Aravind | 3 | Done | Trainer
Sprint 2 | Team 3 | T2-006 | Set up EC2 Instances , Configure VPC & Security groups | Mahesh D | 3 | Done | Norah Elizabeth Biju
Sprint 3 | Team 3 | T3-001 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Iyas K | 4 | Done | Trainer
Sprint 3 | Team 3 | T3-002 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Muhammed Sinan | 4 | Done | Mahesh D
Sprint 3 | Team 3 | T3-003 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Norah Elizabeth Biju | 4 | Done | Trainer
Sprint 3 | Team 3 | T3-004 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Bhogyam venkata sai Likhitha | 4 | Done | Iyas K
Sprint 3 | Team 3 | T3-005 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Ogeti Aravind | 4 | Done | Trainer
Sprint 3 | Team 3 | T3-006 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Mahesh D | 4 | Done | Bhogyam venkata sai Likhitha
Sprint 4 | Team 3 | T4-001 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Iyas K | 6 | Done | Trainer
Sprint 4 | Team 3 | T4-002 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Muhammed Sinan | 6 | Done | Norah Elizabeth Biju
Sprint 4 | Team 3 | T4-003 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Norah Elizabeth Biju | 6 | Done | Trainer
Sprint 4 | Team 3 | T4-004 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Bhogyam venkata sai Likhitha | 6 | Done | Mahesh D
Sprint 4 | Team 3 | T4-005 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Ogeti Aravind | 6 | Done | Trainer
Sprint 4 | Team 3 | T4-006 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Mahesh D | 6 | Done | Iyas K
Sprint 5 | Team 3 | T5-001 | Create Container and deployed image for monolithic application | Iyas K | 4 | Done | Iyas K
Sprint 5 | Team 3 | T5-002 | Create Container and deployed image for monolithic application | Muhammed Sinan | 4 | Done | Trainer
Sprint 5 | Team 3 | T5-003 | Create Container and deployed image for monolithic application | Norah Elizabeth Biju | 4 | Done | Norah Elizabeth Biju
Sprint 5 | Team 3 | T5-004 | Create Container and deployed image for monolithic application | Bhogyam venkata sai Likhitha | 4 | Done | Trainer
Sprint 5 | Team 3 | T5-005 | Create Container and deployed image for monolithic application | Ogeti Aravind | 4 | Done | Mahesh D
Sprint 5 | Team 3 | T5-006 | Create Container and deployed image for monolithic application | Mahesh D | 4 | Done | Trainer
Sprint 6 | Team 3 | T6-001 | Created custom network and deployed microservices in multiple containers | Iyas K | 5 | Done | Mahesh D
Sprint 6 | Team 3 | T6-002 | Created custom network and deployed microservices in multiple containers | Muhammed Sinan | 5 | Done | Trainer
Sprint 6 | Team 3 | T6-003 | Created custom network and deployed microservices in multiple containers | Norah Elizabeth Biju | 5 | Done | Ogeti Aravind
Sprint 6 | Team 3 | T6-004 | Created custom network and deployed microservices in multiple containers | Bhogyam venkata sai Likhitha | 5 | Done | Trainer
Sprint 6 | Team 3 | T6-005 | Created custom network and deployed microservices in multiple containers | Ogeti Aravind | 5 | Done | Muhammed Sinan
Sprint 6 | Team 3 | T6-006 | Created custom network and deployed microservices in multiple containers | Mahesh D | 5 | Done | Trainer
Sprint 7 | Team 3 | T7-001 | Containerized microservice application with services in two different network and initialized a gateway for communication | Iyas K | 5 | Done | Trainer
Sprint 7 | Team 3 | T7-002 | Containerized microservice application with services in two different network and initialized a gateway for communication | Muhammed Sinan | 5 | Done | Mahesh D
Sprint 7 | Team 3 | T7-003 | Containerized microservice application with services in two different network and initialized a gateway for communication | Norah Elizabeth Biju | 5 | Done | Trainer
Sprint 7 | Team 3 | T7-004 | Containerized microservice application with services in two different network and initialized a gateway for communication | Bhogyam venkata sai Likhitha | 5 | Done | Iyas K
Sprint 7 | Team 3 | T7-005 | Containerized microservice application with services in two different network and initialized a gateway for communication | Ogeti Aravind | 5 | Done | Trainer
Sprint 7 | Team 3 | T7-006 | Containerized microservice application with services in two different network and initialized a gateway for communication | Mahesh D | 5 | Done | Bhogyam venkata sai Likhitha
Sprint 8 | Team 3 | T8-001 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Iyas K | 6 | Done | Trainer
Sprint 8 | Team 3 | T8-002 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Muhammed Sinan | 6 | Done | Norah Elizabeth Biju
Sprint 8 | Team 3 | T8-003 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Norah Elizabeth Biju | 6 | Done | Trainer
Sprint 8 | Team 3 | T8-004 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Bhogyam venkata sai Likhitha | 6 | Done | Mahesh D
Sprint 8 | Team 3 | T8-005 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Ogeti Aravind | 6 | Done | Trainer
Sprint 8 | Team 3 | T8-006 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Mahesh D | 6 | Done | Iyas K

## Sprint-Overview(Sample)
Sprint | Sprint Goal | Start Date | End Date | Deliverable
Sprint 1 | VM & Docker Setup | 2026-02-23 | 2026-02-21 | App running in Docker
Sprint 2 | CI/CD Implementation | 2026-02-24 | 2026-02-28 | Working Jenkins pipeline
Sprint 3 | Terraform & Infra | 2026-03-03 | 2026-03-07 | Infra provisioned via Terraform
Sprint 4 | Kubernetes Deployment | 2026-03-10 | 2026-03-14 | App deployed in K8s

## Task_Tracking(Sample)
Sprint | Team | Task ID | Task Description | Assigned To | Story Points | Status | Reviewer
Sprint 1 | Team 1 | T1-001 | Install Ubuntu on EC2 and configure SSH | Arun Simon | 3 | Done | Trainer
Sprint 1 | Team 1 | T1-002 | Setup Git and push sample project to GitHub | Sathvik NB Math | 2 | In Progress | Arun Simon
Sprint 1 | Team 1 | T1-003 | Install Docker and run nginx container | Preethi TK | 3 | Code Review | Trainer
Sprint 1 | Team 2 | T2-001 | Launch EC2 and configure security groups | Gokul | 3 | Done | Trainer
Sprint 1 | Team 2 | T2-002 | Build Docker image for sample Java app | Aswin | 5 | In Progress | Gokul
Sprint 1 | Team 2 | T2-003 | Push Docker image to DockerHub | Johaan | 2 | To Do | -
Sprint 1 | Team 3 | T3-001 | Setup Jenkins on EC2 | Neeraj | 5 | Blocked | Trainer
Sprint 1 | Team 3 | T3-002 | Create basic CI pipeline (Build Stage) | Jayadev | 5 | In Progress | Neeraj
Sprint 1 | Team 4 | T4-001 | Write Terraform script to create EC2 | Chriss Philip Saji | 8 | To Do | Trainer
Sprint 1 | Team 4 | T4-002 | Configure remote backend for Terraform | Abhinav | 5 | Backlog | -